## Overview
WebriQ Central Hub v2.0 — Sprint Plan (All Phases)
Companion to Specification v2.0 · 2-week sprint cadence (Sprint 0 is a 3-week infrastructure sprint) · Status rolls up live from the Sprint Plan sheet
Phase | Name | Sprints | Weeks | Duration (wks) | Goal | Exit Condition | Deliverables | Done | % Complete
Phase 0 | Infrastructure (0A + 0B) | Sprints 0A–0B | 1–4 | 4 | 0A: full v2.0 schema on existing v0.1 DB (§10.6 codebase mapping), auth + role RLS matrix. 0B: event bus, realtime, PWA shell, Resend, KB seed (D24 split). | 0A: migrations green, existing flows still pass. 0B: dummy ticket -> processed event < 60s; shell installable on 3 platforms.
Phase 1A | PM + Desk Core | Sprints 1–3 | 5–10 | 6 | The team's daily work surface: onboarding, native projects/tasks/time, client desk, classification, dev dashboard. | AC1 + AC3 demonstrated; team can run a real project natively.
Phase 1B | HR Core | Sprints 4–5 | 11–14 | 4 | Attendance, leaves, timesheets, announcements — full HR month can run natively. | AC4 + AC5 demonstrated; HR sign-off on balances and derivation.
Phase 1C | AI Loop | Sprints 6–8 | 15–20 | 6 | Assessment, digest, plans, execution + StackShift publish flow, reply, KB seed, unified AI chat, MVP stats page. | AC2 + AC6 + AC7 demonstrated; M14 stats live; hardening green.
Phase 1D | Migration & Cutover | Sprint 9 | 21–22 | 2 | Module-by-module Zoho cutover (HR -> Desk -> Projects), training, MVP exit. | All AC1–AC6 met; Zoho read-only; MVP exit sign-off.
Phase 2 | Assisted Planning | Sprints 10–13 | 23–30 | 8 | Automation toggle, expanded task types, chat actions, circuit breaker, reporting. | 20+ playbooks; classification accuracy > 80%.
Phase 3 | Supervised Autonomy | Sprints 14–17 | 31–38 | 8 | Leave-aware round-robin, multi-dev, calibration, wiki health, gap closure. | Confidence measurably improving; digest rating > 75% Useful.
Phase 4 | Autonomous Operations | Sprint 18+ | 39+ (TBD) | TBD | Trusted tiers, auto-reply window, fine-tuning export, PM handoff. | One customer fully autonomous, 0 failures over 30 days.
TOTAL |  |  |  |  | Weeks 1–38 scheduled (Phase 4 TBD). MVP exit at end of Week 22.

## Sprint Plan
Detailed Sprint Plan — all phases, one row per deliverable
Filter by Phase / Sprint / Module / Owner. Update Status to drive the Overview roll-up. Acceptance checks reference Spec v2.0 AC1–AC6.
Phase | Sprint | Weeks | Milestone | Module / Workstream | Deliverable | Acceptance Check / Notes | Owner | Priority | Status
Phase 0 | Sprint 0A | 1–2 | — | Infrastructure | Supabase project + full v2.0 schema deployed: PM core (projects, tasks, task_comments, attachments, time_logs), Desk (tickets, ticket_messages), HR schema (hr.*, 9 tables), plumbing (event_bus, notifications, notification_preferences, push_subscriptions, audit_logs) + carried-forward AI tables | Schema review signed off; stubs for future phases included to avoid migration debt | Dev Lead | Critical | Not Started
Phase 0 | Sprint 0A | 1–2 | — | Infrastructure | Supabase Auth wired: staff email/password + magic link, client OTP; profiles table with role enum (admin/hr/pm/developer/client) | Test user per role can log in | Dev | Critical | Not Started
Phase 0 | Sprint 0A | 1–2 | — | Security | RLS policies v1 on every table; hr.* policies authored separately and independently reviewed (P9, D19) | RLS test suite passes per role | Dev Lead | Critical | Not Started
Phase 0 | Sprint 0A | 1–2 | — | Codebase Migration | Apply §10.6 mapping to existing v0.1 repo: rename customer_projects -> projects (+ status, dedicated_developers, customer_product_id), widen classification_records.source enum to portal/email/manual/recurring, replace permissive RLS (migration 003) with full role matrix, retire api/webhooks + api/zoho + lib/zoho (keep for 1D import scripts only) | Existing classification + onboarding flows still pass after migrations | Dev Lead | Critical | Not Started
Phase 0 | Sprint 0A | 1–2 | — | Pre-work | Zoho API export access confirmed for Projects/Desk/People (O5) — exports scripted and tested on staging | Dry-run export counts logged | Admin | Critical | Not Started
Phase 0 | Sprint 0B | 3–4 | — | Event Bus | Internal event bus end-to-end: AFTER INSERT triggers on tickets/tasks -> event_bus row -> worker (pg_cron + pg_net, SKIP LOCKED) -> handler stub | Dummy ticket insert produces a processed event in < 60s (replaces Zoho webhook AC) | Dev | Critical | Not Started
Phase 0 | Sprint 0B | 3–4 | — | AI Layer | Vercel AI SDK + Claude API integrated; llm_config table seeded (Haiku/Sonnet per layer); llm_invocation_logs + per-customer cost attribution live from day one | One logged Haiku call with tokens + cost recorded | Dev | High | Not Started
Phase 0 | Sprint 0B | 3–4 | — | Realtime | Supabase Realtime enabled: Postgres Changes on tasks/tickets, Broadcast channel scheme (user:{id}, role:pm), Presence (team:attendance) — proof-of-concept hooks (D16) | Live row change visible in test client < 3s | Dev | High | Not Started
Phase 0 | Sprint 0B | 3–4 | — | PWA Shell | Next.js 16.2.4 App Router (extend existing v0.1 shell) + Serwist service worker + manifest; installable shell on iOS/Android/desktop; app shell layout (sidebar / top bar / bottom tabs) | Install prompt works on 3 platforms | Dev | High | Not Started
Phase 0 | Sprint 0B | 3–4 | — | Email | Resend account + domain verified; React Email base templates; inbound route configured (parked until Sprint 3) | Test transactional email delivered | Dev | Medium | Not Started
Phase 0 | Sprint 0B | 3–4 | — | Knowledge Base | LLM Wiki structure in Supabase Storage; seed Internal KB content (product how-tos, shared Sanity schemas) | Internal KB browsable in admin UI | PM + Dev | Medium | Not Started
Phase 1A | Sprint 1 | 5–6 | M1 | Onboarding | Customer creation flow; customer_id universal key; /onboard/{customer_id} tokenized login-free URL | PM onboards a customer end-to-end in the Hub | Dev | Critical | Not Started
Phase 1A | Sprint 1 | 5–6 | M1 | Onboarding | Dynamic onboarding forms with conditional logic per product (StackShift / PublishForge / CiteForge / PipelineForge); progressive save/resume; file & asset upload to Storage | Form resumes with state intact after browser close | Dev | High | Not Started
Phase 1A | Sprint 1 | 5–6 | M1 | Onboarding | PM dashboard: completion % + missing-fields indicator; customer profile with product instance mapping | — | Dev | High | Not Started
Phase 1A | Sprint 1 | 5–6 | M7 (partial) | Projects | On onboarding completion the Hub auto-creates the native project (replaces Zoho Project creation) | Project appears with correct customer_product link | Dev | High | Not Started
Phase 1A | Sprint 1 | 5–6 | — | Design | Figma Make design system + Auth/Dashboard/Portal frames approved (design kit Prompts 1–4) | Sign-off before Sprint 2 UI build | PM + Design | High | Not Started
Phase 1A | Sprint 2 | 7–8 | M7 | Projects | Native PM core: projects / milestones / tasks / subtasks CRUD; Kanban board (Backlog→Done) with drag-and-drop position; list + calendar views | Board reorder persists and survives refresh | Dev Lead | Critical | Not Started
Phase 1A | Sprint 2 | 7–8 | M7 | Projects | Task detail: rich description (tiptap), priority, multi-assignee, due date, estimate, labels, linked ticket, comments, attachments | — | Dev | High | Not Started
Phase 1A | Sprint 2 | 7–8 | M7 | Realtime | Live board + task updates via Postgres Changes (channel project:{id}); reconcile-on-reconnect hook pattern (P10) | Second client sees a status change < 3s | Dev | High | Not Started
Phase 1A | Sprint 2 | 7–8 | M8 | Time Tracking | Native time_logs: built-in task timer + manual entry; dev day/week hours summary | Timer entry lands in time_logs with source=timer | Dev | High | Not Started
Phase 1A | Sprint 2 | 7–8 | M8 | Time Tracking | PM hours views: by developer / project / task / date range; CSV export | Matches seeded fixture totals exactly | Dev | Medium | Not Started
Phase 1A | Sprint 2 | 7–8 | M7 | Projects | Recurring task templates instantiated by Supabase Cron | Template fires on schedule once | Dev | Medium | Not Started
Phase 1A | Sprint 3 | 9–10 | M2 | Desk | Native ticketing: tickets + ticket_messages, statuses (NEW→CLOSED), SLA timestamps, internal notes visibility | — | Dev Lead | Critical | Not Started
Phase 1A | Sprint 3 | 9–10 | M2 | Desk | Client portal: authenticated request submission (typed forms mapped to Task Taxonomy), attachments, request list + thread view, in-thread replies | Client submits and replies from a phone | Dev | Critical | Not Started
Phase 1A | Sprint 3 | 9–10 | M2 | Desk | Email-to-ticket: Resend Inbound webhook -> ticket/message creation; reply threading via email_message_id | Email to support@ creates a threaded ticket | Dev | High | Not Started
Phase 1A | Sprint 3 | 9–10 | M2 | AI Layer | Classification engine always-on: event bus dispatches ticket.created/task.created -> Haiku -> classification_records (type, priority, llm_eligible, confidence); low-confidence surfaced for PM; manual reclassification UI | AC1: portal request classified in Hub < 60s | Dev | Critical | Not Started
Phase 1A | Sprint 3 | 9–10 | M9 | Dev Dashboard | Developer Today view: assigned tasks/tickets, overdue highlight, team unassigned pool with one-click self-assign (PM notified via Broadcast) | AC3: self-assign fires realtime PM notification | Dev | High | Not Started
Phase 1A | Sprint 3 | 9–10 | M2 | Notifications | Notifications table + in-app inbox + toasts (Broadcast); high-priority classification alert flow; per-user preference matrix v1 | Unread badge + deep link work | Dev | High | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Directory | Employee directory + profiles (hr.employees), manager relationships, HR-only document storage (private bucket, signed URLs) | HR role sees docs; PM/Dev cannot (RLS test) | Dev Lead | Critical | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Attendance | Web clock-in/out from PWA: hr.attendance_punches with timestamp, optional geo/IP per policy (O3), device fingerprint | Punch from mobile recorded < 2s | Dev | Critical | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Attendance | Offline punch queue: IndexedDB queue + sync-on-reconnect (D22); 'punch saved, will sync' state | Airplane-mode punch syncs on reconnect | Dev | High | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Attendance | Nightly derivation cron: punches + leaves + holidays -> hr.attendance_days (PRESENT/LATE/HALF_DAY/ABSENT/ON_LEAVE/HOLIDAY); correction request -> approval -> audit log | Derived day matches manual calc on 20 fixtures | Dev | High | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Attendance | HR dashboard: daily grid, late/absence trends, CSV/XLSX export; Presence channel 'clocked in' indicator | — | Dev | Medium | Not Started
Phase 1B | Sprint 4 | 11–12 | M11 | HR — Comms | Announcements feed: pinned posts, read receipts, realtime + push delivery | — | Dev | Medium | Not Started
Phase 1B | Sprint 4 | 11–12 | — | HR — Policy | PH holiday calendar 2026–2027 seeded (O8); attendance policy parameters configured (O3) | HR sign-off | HR | High | Not Started
Phase 1B | Sprint 5 | 13–14 | M11 | HR — Leave | Leave types + accrual rules engine (table-driven, jsonb rules); monthly accrual cron; carry-over caps | Accrual run matches HR-approved expectations (O2) | Dev Lead | Critical | Not Started
Phase 1B | Sprint 5 | 13–14 | M11 | HR — Leave | Leave request flow: file (half-day support, attachments) -> manager approve/reject with reason -> balance auto-deduct -> team calendar + assignment-pool eligibility update | AC4 end-to-end on mobile | Dev | Critical | Not Started
Phase 1B | Sprint 5 | 13–14 | M11 | HR — Leave | Team leave calendar for PMs (dates only per P9); leave.approved event handler refreshes round-robin pool data | — | Dev | High | Not Started
Phase 1B | Sprint 5 | 13–14 | M11 | HR — Timesheets | Weekly timesheet: auto-filled from time_logs + attendance; submit -> approve -> locked; payroll CSV/XLSX export (D21) | AC5: payroll-period export with zero Zoho reference | Dev | Critical | Not Started
Phase 1B | Sprint 5 | 13–14 | M11 | Notifications | Web Push end-to-end (service worker): leave decisions, HIGH/CRITICAL alerts; push_subscriptions mgmt; HR request types (COE, equipment) with simple routing | Push received with app closed | Dev | High | Not Started
Phase 1B | Sprint 5 | 13–14 | — | Parallel option | Decision gate: run Phase 1C in parallel from Sprint 6 with second workstream? (O10) | Mgmt decision recorded | Mgmt | Medium | Not Started
Phase 1C | Sprint 6 | 15–16 | M3 | AI Layer | Requirements Assessment (Sonnet): CLEAR/PARTIAL/BLOCKED subtask breakdown; requirements_assessments records; clarification draft for PM; auto re-assessment on client reply | Blocked task flags CLARIFICATION_NEEDED in digest | Dev Lead | Critical | Not Started
Phase 1C | Sprint 6 | 15–16 | M3 | AI Layer | buildContextChain(classificationId) shared utility — full chain (ticket -> classification -> assessment -> clarifications) feeds every Sonnet prompt (P6). Build here, not later. | Chain snapshot stored per invocation | Dev | Critical | Not Started
Phase 1C | Sprint 6 | 15–16 | M4 | AI Layer | Daily Digest (Haiku) via Supabase Cron -> digest_logs; PM digest (pending, unassigned, stalled, automation queue, ready-to-close) + Dev digest; one-tap Useful/Partial/Not Useful rating | Digest renders from precompiled record (no live LLM call) | Dev | High | Not Started
Phase 1C | Sprint 6 | 15–16 | M4 | HR x AI | Digest HR signals for managers: on leave today, pending approvals, missing timesheets, attendance exceptions | — | Dev | Medium | Not Started
Phase 1C | Sprint 6 | 15–16 | M14 | Reporting | MVP Stats page (read-only, D25): hours by developer/project, task throughput (created vs completed/week), ticket volume + SLA hit rate, attendance summary — Supabase views + simple charts | Leadership view live from Week 16 | Dev | High | Not Started
Phase 1C | Sprint 7 | 17–18 | M5 | AI Layer | Plan Generation (Sonnet): steps, affected files, risk flags, confidence; human approval gate UI with structured rejection reasons; plan-approval Broadcast to role:pm | Plan approve/reject round-trip stored | Dev Lead | Critical | Not Started
Phase 1C | Sprint 7 | 17–18 | M13 (v1) | Ops Chat | Unified AI Chat v1: global panel + Cmd/Ctrl-K palette; AI SDK streaming endpoint /api/ai/chat; role-scoped tool registry for PM + Dev read tools (pending/priority tasks, SLA, hours, my tasks); answers as cards with deep links | PM asks 'how many tasks are pending?' and gets a correct linked answer | Dev | High | Not Started
Phase 1C | Sprint 7 | 17–18 | M10 | Knowledge Base | Customer KB scaffold (per-tenant specs, code map); seed playbooks for CONTENT_UPDATE + SETTINGS_CHANGE; weekly Wiki Lint cron | Lint report lands in admin UI | Dev | Medium | Not Started
Phase 1C | Sprint 7 | 17–18 | M10 | Knowledge Base | HR-policy wiki pages in Internal KB (feeds HR Assistant + chat answers) | — | HR + PM | Medium | Not Started
Phase 1C | Sprint 8 | 19–20 | M6 | Execution | Execution engine (Sonnet): Sanity API mode (per-tenant sanity_project_id), GitHub PR mode (branch/commit/PR via Actions + Claude Code), Product API (MCP) mode; pre_action_states for revert; PARTIAL_EXECUTION never auto-retried; circuit breaker (3 fails -> pause per customer) | AC2: CONTENT_UPDATE full loop without leaving Hub | Dev Lead | Critical | Not Started
Phase 1C | Sprint 8 | 19–20 | M6 | Execution | GitHub webhook -> PR status + Vercel/Netlify preview URL displayed on task | Preview link visible on task card | Dev | High | Not Started
Phase 1C | Sprint 8 | 19–20 | M6 | Execution | US-PUB-1 Publish to StackShift dev URL: PM 'Publish to dev' action on content tasks -> Sanity publish -> StackShift staging rebuild (deploy hook) -> dev URL captured to tasks.preview_url, shown as Dev-preview chip + included in client reply draft; retryable, revertible (P5) | AC7: dev URL on task + in reply within one rebuild cycle | Dev Lead | Critical | Not Started
Phase 1C | Sprint 8 | 19–20 | M6 | AI Layer | Reply Generation (Haiku) on COMPLETED; PM review/edit (diffs stored); send via Resend threaded into ticket + portal | Client receives threaded reply | Dev | High | Not Started
Phase 1C | Sprint 8 | 19–20 | M13 | Ops Chat | Ops Chat complete: HR/manager + Admin tool groups (who filed leaves, absences, approvals, LLM cost), LLM Wiki retrieval grounding, answer rating -> llm_invocation_logs, mobile chat sheet | AC6: 'priority tasks + who is absent?' answered RLS-scoped with links | Dev | Critical | Not Started
Phase 1C | Sprint 8 | 19–20 | — | Hardening | Load/perf pass: event bus p95, realtime delivery < 3s, RLS regression suite, soft token budgets + PM alert | Targets green on staging | Dev Lead | High | Not Started
Phase 1D | Sprint 9 | 21–22 | M12 | Migration | HR cutover at month boundary: employees, leave types, opening balances (HR signed-off, O2), 12-mo attendance summary import (source=zoho_import); Zoho People -> read-only | Balances reconciled to the day | Dev Lead | Critical | Not Started
Phase 1D | Sprint 9 | 21–22 | M12 | Migration | Desk cutover: new support address live; Zoho Desk auto-responder redirect; open tickets + threads + attachments imported | No client request lost during switch | Dev | Critical | Not Started
Phase 1D | Sprint 9 | 21–22 | M12 | Migration | Projects cutover: freeze Friday EOD -> weekend import (projects, tasks, time logs; PM-signed status/priority mapping per O12; zoho_legacy_id in meta) -> Monday live | Team works fully in Hub Monday | Dev Lead | Critical | Not Started
Phase 1D | Sprint 9 | 21–22 | M12 | Migration | Zoho read-only 60-day tail scheduled; archived exports to cold storage; license cancellation calendared (D18) | Checklist complete | Admin | High | Not Started
Phase 1D | Sprint 9 | 21–22 | — | Enablement | Team training (PM/Dev/HR tracks) + client portal announcement email; runbook + on-call rota for cutover fortnight | All staff completed walkthrough | PM | High | Not Started
Phase 1D | Sprint 9 | 21–22 | — | Exit Gate | MVP exit review: AC1–AC6 demonstrated; metrics baseline captured | Mgmt sign-off | Mgmt | Critical | Not Started
Phase 2 | Sprint 10 | 23–24 | — | Automation | Automation toggle per customer: plan auto-triggers on CLEAR assessment when ON | Toggle honored; OFF = manual unchanged | Dev Lead | High | Not Started
Phase 2 | Sprint 10 | 23–24 | — | Automation | Expanded task types live: SETTINGS_CHANGE, SEO_UPDATE, ASSET_UPLOAD execution paths | One real execution per new type | Dev | High | Not Started
Phase 2 | Sprint 11 | 25–26 | — | Ops Chat | Chat actions v1 behind explicit confirmation (P8): assign task, approve leave, change status — from chat with confirm dialog + audit log (7J Phase-2 commitment) | Action requires confirm; logged to audit_logs | Dev | High | Not Started
Phase 2 | Sprint 11 | 25–26 | — | Learning Loop | Playbook library UI: accumulate from real executions; rejection-reason data feeding KB gap identification | 20+ playbooks visible with usage counts | Dev | Medium | Not Started
Phase 2 | Sprint 12 | 27–28 | — | Reliability | Per-customer circuit breaker hardening + failure analytics; PARTIAL_EXECUTION triage queue | 3 consecutive failures auto-pause verified | Dev | High | Not Started
Phase 2 | Sprint 12 | 27–28 | — | Reporting | Reporting dashboard: classification accuracy, plan approval rate, reply edit rate, SLA hit rate, chat answer accuracy | Metrics match llm_invocation_logs ground truth | Dev | Medium | Not Started
Phase 2 | Sprint 13 | 29–30 | — | Exit Gate | Phase 2 exit: 20+ executions in playbook library; classification accuracy > 80%; chat answer accuracy > 85% | Mgmt review | Mgmt | Critical | Not Started
Phase 3 | Sprint 14 | 31–32 | — | Assignment | Round-robin auto-assignment: pool excludes devs on approved leave (native HR check), dedicated-client devs, and over load threshold (O11); assignment reason logged | Assignment skips on-leave dev in test | Dev Lead | High | Not Started
Phase 3 | Sprint 15 | 33–34 | — | Assignment | Multi-developer assignment per task; workload-aware balancing with PM-configurable thresholds | — | Dev | High | Not Started
Phase 3 | Sprint 16 | 35–36 | — | Calibration | Confidence calibration reporting (predicted vs actual outcomes); wiki health dashboard (stale content, lint findings, KB coverage) | Calibration chart trending in reports | Dev | Medium | Not Started
Phase 3 | Sprint 17 | 37–38 | — | Learning Loop | Knowledge gap closure workflow: rejection -> KB stub -> PM fills -> re-test | One gap closed end-to-end | Dev | Medium | Not Started
Phase 3 | Sprint 17 | 37–38 | — | Exit Gate | Phase 3 exit: confidence measurably improving; digest rating > 75% Useful | Mgmt review | Mgmt | Critical | Not Started
Phase 4 | Sprint 18+ | 39+ (TBD) | — | Autonomy | Full autonomous execution for Tier 3 customers (PM notified post-execution) | 0 failures over 30 days for one customer | Dev Lead | High | Not Started
Phase 4 | Sprint 18+ | 39+ (TBD) | — | Autonomy | Auto-send reply with configurable review window | — | Dev | High | Not Started
Phase 4 | Sprint 18+ | 39+ (TBD) | — | Learning Loop | LLM Wiki fine-tuning data export; cross-customer pattern recognition from aggregate execution data | — | Dev | Medium | Not Started
Phase 4 | Sprint 18+ | 39+ (TBD) | — | Enablement | PM Handoff briefing: one-click project briefing generation for new PMs | — | Dev | Medium | Not Started
Phase 4 | Sprint 18+ | 39+ (TBD) | — | Exit Gate | Phase 4 exit: one customer at full autonomous tier, 0 failures over 30 days | Mgmt review | Mgmt | Critical | Not Started

## Milestones & ACs
MVP Milestones (M1–M13) and Acceptance Criteria (AC1–AC6)
ID | Name | Scope Summary | Sprint(s) | Phase
M1 | Customer & Onboarding | Customer creation, tokenized onboarding URL, dynamic forms, profile + product mapping | Sprint 1 | Phase 1A
M2 | Native Desk + Classification | Portal + email-to-ticket; classification < 60s; reclassification UI | Sprint 3 | Phase 1A
M3 | Requirements Assessment | CLEAR/PARTIAL/BLOCKED, clarification drafts, re-assessment on reply | Sprint 6 | Phase 1C
M4 | Daily Digest | Precompiled digest_logs + ratings + HR signals for managers | Sprint 6 | Phase 1C
M5 | Plan Generation (manual) | Plans with risk flags + human approval gate, structured rejections | Sprint 7 | Phase 1C
M6 | Execution + Reply | Sanity / GitHub PR / MCP modes, revert, circuit breaker; Haiku replies via Resend | Sprint 8 | Phase 1C
M7 | Native Project Management | Projects auto-create, Kanban/list/calendar, comments, attachments, live boards | Sprints 1–2 | Phase 1A
M8 | Time Tracking | Timer + manual time_logs, PM hours queries, export | Sprint 2 | Phase 1A
M9 | Developer Dashboard | Today view, team pool self-assign, hours, prompt queries | Sprint 3 | Phase 1A
M10 | LLM Wiki Seed | Internal + Customer KB scaffold, seed playbooks, Wiki Lint cron, HR policy pages | Sprint 7 | Phase 1C
M11 | HR Core | Directory, clock in/out (offline-queued), derived attendance, leaves + balances, timesheets, announcements, push | Sprints 4–5 | Phase 1B
M12 | Migration Complete | HR -> Desk -> Projects cutovers; Zoho read-only | Sprint 9 | Phase 1D
M13 | Unified AI Chat | Global panel + Cmd-K, role-scoped tools across PM/Desk/HR, KB-grounded answers, deep links, ratings | Sprints 7–8 | Phase 1C
M14 | MVP Stats Page | Read-only: hours by dev/project, task throughput, ticket volume + SLA, attendance summary (D25) | Sprint 6 | Phase 1C
AC | Acceptance Criterion | Proven in
AC1 | Client submits a request from a phone via the portal; PM sees it classified in the Hub within 60 seconds. | Sprint 3
AC2 | A CONTENT_UPDATE completes classify -> plan -> approve -> execute -> client reply without leaving the Hub. | Sprint 8
AC3 | Developer self-assigns from the team pool; PM gets a realtime notification; hours appear in PM hours view. | Sprint 3
AC4 | Employee clocks in on mobile, files a half-day leave, gets approval — balance, calendar, and pool update automatically. | Sprint 5
AC5 | Full payroll-period timesheet export produced from Hub data with zero reference to Zoho. | Sprint 5
AC6 | PM asks the chat 'what are today's priority tasks, and who is absent?' and gets an accurate, RLS-scoped answer with links. | Sprint 8
AC7 | PM clicks 'Publish to dev' on a completed content task; dev URL appears on the task and in the drafted client reply (US-PUB-1). | Sprint 8

## Timeline
Timeline — Weeks 1–38 (Phase 4 TBD)
One row per sprint; colored cells = active weeks. MVP exit marker at Week 22.
Sprint | Focus | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Sprint 0A | Schema + auth + RLS + codebase mapping
Sprint 0B | Event bus + realtime + PWA + Resend + KB
Sprint 1 | Onboarding + customer hub (M1)
Sprint 2 | Native PM + time tracking (M7, M8)
Sprint 3 | Desk + classification + dev dashboard (M2, M9)
Sprint 4 | Directory + attendance + announcements (M11)
Sprint 5 | Leaves + timesheets + push (M11)
Sprint 6 | Assessment + digest + stats page (M3, M4, M14)
Sprint 7 | Plans + Ops Chat v1 + KB seed (M5, M13, M10)
Sprint 8 | Execution + publish flow + reply + chat complete (M6, M13)
Sprint 9 | Zoho migration + training + MVP exit (M12)
Sprint 10 | Automation toggle + new task types
Sprint 11 | Chat actions + playbook library
Sprint 12 | Circuit breaker + reporting
Sprint 13 | Phase 2 exit gate
Sprint 14 | Leave-aware round-robin
Sprint 15 | Multi-dev + workload balancing
Sprint 16 | Calibration + wiki health
Sprint 17 | Gap closure + Phase 3 exit
| Legend: | 0 |  | 1A |  | 1B |  | 1C |  | 1D |  | 2 |  | 3 |  | Week 22 = MVP exit (red header)

## Open Items
Open Items — must-resolve-by sprint gates
# | Item | Owner | Priority | Resolve before | Status
O1 | Final Task Type Taxonomy incl. HR_REQUEST sub-types | PM + HR | HIGH | Sprint 3 | Open
O2 | Leave accrual rules + opening balance sign-off (per employee) | HR | HIGH | Sprint 5 | Open
O3 | Attendance policy: grace period, geolocation on/off, correction window | HR + Mgmt | HIGH | Sprint 4 | Open
O4 | Support email address + Resend Inbound domain setup | Dev | HIGH | Sprint 3 | Open
O5 | Zoho API export access for all five products (before licenses lapse) | Admin | HIGH | Sprint 0A | Open
O6 | SLA matrix per priority for the Desk | PM | MEDIUM | Sprint 3 | Open
O7 | Notification preference defaults per role | PM | MEDIUM | Sprint 3 | Open
O8 | PH holiday calendar 2026–2027 seed data | HR | MEDIUM | Sprint 4 | Open
O9 | Client portal auth mode: magic link only vs optional password | PM | MEDIUM | Sprint 3 | Open
O10 | 1B/1C parallel workstreams vs sequential (staffing) | Mgmt | MEDIUM | Before Sprint 4 | Open
O11 | Round-robin load threshold defaults | PM | MEDIUM | Sprint 14 | Open
O12 | Zoho -> Hub task status & priority mapping table reviewed + signed off by PM before migration dry run (data fidelity) | PM | HIGH | Sprint 9 | Open